## Sheet1
Week | Project: Flask | Estimated hours | Best Estimated Hours | Worst estimated hours | Description
2021-03-08 | Tasks before coding | 8 | 4 | 10 | Set up Azure Portal, Azure DevOps, Github repository, weekly and Trello board
2021-03-15 | Code solution | 16 | 20 | 10 | Implement solution in python
2021-03-22 | Develop and verify Makefile | 4 | 2 | 6 | Develop and verify Makefile in local env
2021-03-29 | Set Ups Azure Portal | 2 | 1 | 4 | Connect and configure Azure Portal with the project
2021-04-05 | Deploy solution | 1 | 1 | 2 | Deploy the solution in a webapp
2021-04-12 | Connect pipelines with cloud environment | 4 | 2 | 6 | Connect Github, Azure Pipelines, and Azure cloud (portal)
2021-04-19 | Verify deployment | 2 | 1 | 4 | Verify that the deployment was successful with pylint and pytest
2021-04-26 | Deploy in production | 4 | 2 | 6 | If all of the above is met, it is deployed in a productive environment
2021-05-03 | Dry run | 16 | 16 | 16 | A complete monitoring is carried out after the transition to production to verify correct operation
2021-05-10 | Add new features | TBD | TBD | TBD | New features
2021-05-17 | Start maintenance | TBD | TBD | TBD | In case of requiring improvements
2021-05-24
| Goals | Goals
Deploy Flask App
Perform CI/CD to deploy code
Always check code status before deploying
Automate everything